## Slide 1: National Fish & Wildlife Foundation
Christina Kakoyannis
Director, Strategic Planning & Evaluation
CMP Technical Meeting – Bright Spot
October 2014

## Slide 2
Develop long-term, science-based conservation initiatives with measurable outcomes that “move the needle” for key species, places of importance, or issues
2006 NFWF Board Mandate

## Slide 3: Open Standards

## Slide 4: Product of Planning Effort
Business Plan that guides initiative grantmaking

## Slide 5: Implementation
  Grantmaking: Fund grants aligned with plan
  Monitoring:
    Applicants provide estimates for indicators
    Grantees update data

## Slide 6: Step 4. Analyze, Use, Adapt
  Rapid Assessments
  Third-party evaluations
  Annual Scorecards

## Slide 7: Initiative Scorecards
  Snapshot of key metrics:
    Funding
    Conservation progress

## Slide 8: Scorecard

## Slide 9
No progress on road decommisioning objective.
Perhaps solicit some proposals for this.
Better than expected progress.
Perhaps allocate funds elsewhere.

## Slide 10: Internal Rapid Assessment
Assessment Criteria:
Implementation Process
Conservation Progress
Long-Term Sustainability
Bridled Terns (photo courtesy of Island Conservation)
Lessons Learned, including broader impacts
Review of business plan

## Slide 11: I. Implementation Progress
Funding of Strategies
  Actual spending in line with budget?
  % of NFWF’s investment from funding sources?
Implementation of Strategies
  Key strategies/activities implemented?
  Grant progress expected?
  Alignment of grant portfolio with plan?
Monitoring & Evaluation
  Systematic monitoring of implementation, outcomes, and focal species?

## Slide 12: Addressing Recommendations
Rec # | Recommendation | Priority | Action | Status
1 | Business plan should include quantitative outcome targets | High | Developed targets for scorecard. Hired monitoring person. | Complete
2 | Lead an effort to have organizations share demographic data & meta-analyses | Medium | Hired monitoring person will engage on this | In progress
3 | Consider broadening single species focus to increase partner participation | High | Working on having as focal species of other initiatives | In progress

## Slide 13: Commission Third-Party Evaluations
Develop NFWF response to evaluation recommendations

## Slide 14
  Rapid Assessments
  Third-party Evaluations
  Scorecard
Levels of Assessment
Depth & Resources required
Frequency

## Slide 15: Thanks